## TGIF Conference Cost Worksheet
WBS | Name | Duration () | Work () | Cost ($s) | Notes
1 | TGIF AI Conference | 186 days | 1,584.4 hours | 295197.1993 | All Estimates Below give an 80-20 split for lowest-highest paid employees
1.1 | Planning | 50 days | 222 hours | 6472.8
1.1.1 | Agenda/Content | 30 days | 50.4 hours | 696 | 80% of work done by Content Team, 20% by PMO (Applies to all planning)
1.1.2 | Location Selection | 30 days | 22.8 hours | 1322.4
1.1.3 | Speaker Strategy | 20 days | 30.4 hours | 371.2
1.1.4 | Attendee Strategy | 20 days | 30.4 hours | 371.2
1.1.5 | Vendors/Sponsors | 20 days | 88 hours | 3712
1.2 | Content (Speakers/Experts) | 70 days | 76 hours | 881.6
1.2.1 | Identifying | 60 days | 72 hours | 835.2
1.2.1.1 | Academia | 60 days | 24 hours | 278.4 | 80% of work done by Content Team, 20% by PMO (Applies to all Identifying)
1.2.1.2 | Industry | 60 days | 24 hours | 278.4
1.2.1.3 | Public Sector | 60 days | 24 hours | 278.4
1.2.2 | Confirming | 10 days | 4 hours | 46.4
1.3 | Partnerships/Procurement | 20 days | 80 hours | 4640
1.3.1 | Tech companies | 10 days | 40 hours | 2320 | Assuming the firm has to find and contact companies and vendors plus the work on the of the conference. A 4 person team with 1 senior member
1.3.2 | AI Vendors | 20 days | 40 hours | 2320
1.4 | Attendee Management | 130 days | 172 hours | 7080
1.4.1 | Guest List | 40 days | 25.6 hours | 1024 | -Before 10 of the event, make final list of the guests -2 to 3 staff members required for this task
1.4.2 | RSVPs | 50 days | 28 hours | 1120 | -Start sending emails to the guests confirming their attendance -Tentatively this should be done 10 before the event -5 staff members required to handle this
1.4.3 | Handouts | 30 days | 38.4 hours | 1656 | -Design the Handouts atleast 20 before the conference -Print these handouts and distribute them
1.4.4 | Special Needs | 40 days | 80 hours | 3280 | -Ask all the registered members if they have any special needs like travel allowance, handicap needs or any other -Make arrangements according to these needs -80% of work done by Content Team, 20% by PMO
1.5 | Marketing/Communications | 110 days | 680.8 hours | 32272
1.5.1 | Physical | 60 days | 192 hours | 7680 | It would probably take 3 months to design, approve and make changes to the signage with 1 senior employee and 2 junior. Taking the average cost as $40
1.5.2 | Onliine | 100 days | 280 hours | 16240 | This would take longer as the social media marketing is done till the very end of the event.
1.5.3 | PR | 30 days | 48 hours | 1920 | 3 junior level employees
1.5.4 | Press/Media | 30 days | 120 hours | 4800
1.5.5 | Merchandise | 2 days | 8.8 hours | 352
1.5.6 | Feedback/Sales Analysis | 10 days | 32 hours | 1280 | 2 employees
1.6 | Conference Operations | 93 days | 12 hours | 228070
1.6.1 | Venue | 93 days | 0 hours | 223790 | Considering a split of 80-20 on the employee and their wages.
1.6.1.1 | Booking | 4 days | 0 hours | 53720 | I was not sure where to add the cost of booking the venue. $50000 for 3 in this case. (0.8*40+0.2*150)*60+50000
1.6.1.2 | Rooms and Equipment | 3 days | 0 hours | 54960 | $50000 for accommodations of 600 attendees.
1.6.1.3 | Tables/Chairs | 3 days | 0 hours | 4160 | 2200 chairs and 50 tables= 2200+100=2300
1.6.1.4 | Decorations | 3 days | 0 hours | 1390 | 30-70 split of the higher and lower level staff because supervisors are important here.
1.6.1.5 | Music | 3 days | 0 hours | 4360 | 14 speaker system with microphones for 2000 people. 60 per speaker system. 3 . $2500
1.6.1.6 | Lighting | 3 days | 0 hours | 4500
1.6.1.7 | Furnishing | 3 days | 0 hours | 0 | Chairs and Tables have already been covered
1.6.1.8 | Signage | 3 days | 0 hours | 4500
1.6.1.9 | Food and Beverage | 3 days | 0 hours | 96200 | $30 per person per of food expenses.
1.6.2 | Security | 3 days | 0 hours | 2480
1.6.3 | Technology | 1 day | 12 hours | 1800
1.6.3.1 | Live Streaming | 1 day | 5.6 hours | 840
1.6.3.2 | Audio/Visual | 1 day | 6.4 hours | 960 | $2400 for 8 projector sets for 3
1.7 | Administration | 134 days | 338.4 hours | 15595.1993
1.7.1 | Staffing (Volutneers/Workers) | 4 days | 114.4 hours | 6635.2
1.7.1.1 | Ticketing | 2 days | 9.6 hours | 556.8 | -Assuming that the conference is 8 long daily (maybe 9:00 a.m. to 5 p.m.) -Ticketing can stop around 4p.m. -No ticket selling or registration should be done after 3p.m. on the last
1.7.1.2 | Security | 3 days | 13.2 hours | 765.6 | -Security needed for all 8 of the conference -Planning and fixing security can take about a week's time because it is outsourced
1.7.1.3 | Tables Set Up | 1 day | 8 hours | 464 | -Table set up will take place on the 1st
1.7.1.4 | MC/Hosts | 3 days | 14.4 hours | 835.2 | -Hosts are hired for 3 , 8 a -Booking hosts will require a week's time
1.7.1.5 | Photography | 3 days | 13.2 hours | 765.6 | -Photogrpahers have to be hired for 3 , 8 per -Booking photographers can take about 5 .
1.7.1.6 | Caterers | 3 days | 24 hours | 1392 | -Caterers are hired for 3 , 10 a . -Hotel's caterer service is being availed so not much planning will go into booking catering -No catering service would be needed for Dinner for the 3rd .
1.7.1.7 | Cleaning Staff | 3 days | 24 hours | 1392 | -Cleaning staff will be hired for all 3 . -Additional work is assigned the before the conference. -Working for the cleaning staff will be 10 a -Hotel's cleaning staff will be availed for this activity so no additional planning is needed for this activity
1.7.1.8 | Breakdown | 1 day | 8 hours | 464 | -Breakdown should take place after the end of the conference -It should ideally take only one
1.7.2 | Budget | 133 days | 224 hours | 8959.9993
1.7.2.1 | Revenue | 130 days | 160 hours | 6400 | -For finding the revenue generated, we will have to check costs of ticket management and sposor management
1.7.2.1.1 | Ticket MGMT | 90 days | 64 hours | 2560 | -Ticket Management would require work few before the conference and 1-2 after that -The amount of tickets should be enough and there should be on the spot registration tickets available for guests who have not registered yet
1.7.2.1.2 | Sponsor MGMT | 130 days | 96 hours | 3840 | -Take reviews from sponsors -Make sure everything went according to the contract -This will require around 30 to find the sponsors, budget the cost associated with them and bring them in a contract -Around 10 to manage the deliverables and end the contract
1.7.2.2 | Expenses | 133 days | 64 hours | 2559.9993 | -After conference, calculate the expenses -Ideally this should not take more than 5
1.8 | Project Close-Out | 2 days | 3.2 hours | 185.6 | -Make the remaining payments -Finally calculate the total expenses and total earnings of the conference